## SELF ASSESSMENT
Good Practice Project Management Self Assessment Tool
| Project Details |  | Self Assessment Overall Results
| Office |  | Design | 0
| Project Name |  | M&E and Learning | 0
|  |  | Capacity and Finance | 0
| Project Number |  | Beneficiaries and Indigenous People | 0
| Completed By |  | Strategic Partnerships (Govt/Private) | 0
|  |  | Risk Management and Sustainability | 0
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| SCOPE & VISION |  | Broadly speaking, what boundaries define the focus of the project and what is the ultimate state we are working to achieve?
| SCOPE The project has a clearly articulated scope (geographic and thematic) | Scope and vision text have been documented and shared in plans and supported where necessary with maps, issues papers etc. as appropriate. Relevance of the scope is clear and any key areas of strategic focus are defined. | Scope and vision text have been documented and shared, with simple supporting documentation. Relevance of the scope is clear. | Evidence that scope has been considered and documented in plans. | Scope not yet defined but activities have been put in place to decide scope i.e. workshops etc. | Scope not defined or considered
| VISION The project partners have a shared vision of the desired outcome | A shared vision has been reached. The vision of what good looks like has been developed with the relevant stakeholder engagement which may include poor and marginalised constituencies amongst others. Vision/ purpose and scope uses gender sensitive or inclusive language. | The vision of what good looks like has been shared with the relevant stakeholders (or the strategy for reaching a shared vision is being implemented). This may include poor and marginalised constituencies amongst others. | The vision is general, relatively brief, visionary and audience appropriate. It has not been shared, but there is a strategy for reaching a shared vision. | Vision does not relate to the goal or targets or is inappropriate for audience (or there is no strategy for achieving a shared vision). | No vision
| CONSERVATION TARGETS |  | Precisely what is to be affected in a positive way by the project, and is this clearly linked to biodiversity (and human wellbeing)?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| (CONSERVATION) TARGETS The project has a clear justification of what they want to conserve (biodiversity targets), or the footprint element/ threat they wish to reduce and how that relates to biodiversity. And if appropriate how this would impact human wellbeing positively (human wellbeing targets identified). | A clear and specific list of the species and habitats that are the focal conservation targets is documented and clearly justified in relation to the scope. Or for thematic projects, the project has clearly identified the footprint element/ threat to be addressed and has explained how this relates to biodiversity. Current and desired condition of the targets has been defined e.g. through viability assessment. Project considerations: the project has clearly defined the beneficiaries, for example - those people living in poverty dependent on the ecosystems | A clear and specific list of the species and habitats that are the focal conservation targets is documented and clearly justified in relation to the scope. Or for thematic projects, the project has clearly identified the footprint element/ threat to be addressed and has explained how this relates to biodiversity. | There is a list of conservation targets or footprint elements and/ or a dedicated section on these in the plan or project documents. However there is limited justification provided. | There is no list and/or dedicated section of a document regarding conservation targets or footprint elements. However targets are discernible in documentation and/ or can be identified from direct discussion with project staff | No conservation targets are discernible and project staff are unaware or unable to describe them
| Hint: | Evidence to support for this section may be found in project plan, proposals, concepts, viability assessments, GPF priority lists etc.
| CONTEXT & STAKEHOLDERS |  | What forces, factors and actors most powerfully affect the conservation targets either positively or negatively and what are the relationships among them?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| CONTEXT The project has a clear and comprehensive understanding of the context (including the political, social, economic, climate, environmental and institutional systems) affecting its conservation targets. The project has prioritised the most important threats for priority action. And stakeholders within the context have been identified at relevant points | Based upon through assessments, there is a clear and comprehensive understanding of context affecting the scope and targets, including drivers, threats, opportunities and their interlinkages. Priority factors to be addressed are clear and justified. The main stakeholders which affect or are affected by the above aspects and inter- relationships are described, which can include poor and marginalised communities. Climate vulnerabilities (both human and ecosystem) within the context have been described and analysed. | There is evidence of discussion of context and this has been captured or documented. Thinking and decisions have been based upon some kind of data/evidence supported analysis. Key interlinkages are discussed and priorities are clear and justified Climate vulnerabilities within the context have been identified. | There is evidence of discussion of context but this evidence indicates that the complexity of the context is not fully comprehended. However this has been recognised and further work is scheduled to undertake greater analysis before priorities for focus and action are set. Climate vulnerabilities within the context have been discussed, based on available literature/science. | Analysis of context is very basic and general, with relationships between factors not understood in detail. Priorities for focus and action are not very clearly defined or justified | There is little or no evidence or understanding of the context
| STAKEHOLDERS The project has a clear and comprehensive understanding of stakeholders affecting or affected by the project and has either identified or is taking strategic steps to engage them | Based upon through assessments, there is a clear and comprehensive understanding of the stakeholders affecting or affected by the context (above). Key stakeholders have a shared understanding of this context. Allies or barriers in relation to potential strategies have been identified as necessary. Project considerations: All stakeholders whose influence and interests may conflict with poorer marginalised groups have been identified. Explicit strategies for engaging each stakeholder group are described. | There is evidence of discussion of stakeholders and with stakeholders and this has been captured and documented. Key stakeholder relationships have been discussed and are somewhat clear and justified. | There is evidence of discussion of stakeholders but this evidence indicates that the complexity of the relationships/needs/roles of the stakeholders is not fully comprehended. However this has been recognised and further work is scheduled to undertake greater analysis before priorities for focus and action are set | Analysis of stakeholders is very basic and general. Priorities for focus and action are not clearly defined or justified | There is little or no evidence or understanding of the stakeholders involved
| BENEFICIARIES AND INDIGENOUS PEOPLE Within the broader ‘stakeholder’ group, special attention is required on key intended beneficiaries or the ‘target population/group’ as well as indigenous people. | As under level 4, plus: Consulted with potential beneficiaries (via legitimate representatives) from the outset and received their agreement for interventions. Provided on-going fora for consultation, and opportunities for involvement in the project for key stakeholders/beneficiaries. Ensured that partnerships with national governments, donor agencies, private corporations and other NGOs have served to protect or promote: local rights to access/ownership; beneficiary involvement in and capacity to manage the environment. Climate and other vulnerabilities of stakeholders have been identfied and analysed through participatory processes with stakeholders. | Through consultative and participatory approaches, understand particularly poor and marginalised groups and individuals, and understand how the project will potentially affect these groups/individuals. Traditional and customary user rights in terms of ownership and access are understood and observed, including an understanding of gender-specific needs and issues. Intervention design reflects this. Refrained from supporting activities that have not got support or buy-in. Climate vulnerabilities of stakeholders have been identified with stakeholders. | Key beneficiaries, target groups and/ or indigenous groups identified. Some understanding of these poor and marginalised groups and how the project could affect them. | Key beneficiaries, target groups and/ or indigenous groups identified. | Key beneficiaries, target groups and/ or indigenous groups not identified.
| Hint: | Evidence to support this section may be found in project plan, proposals or concepts as a detailed narrative or graphical illustration such as a conceptual model; other supporting evidence includes threat ranking; stakeholder analysis; use of PRA tools where relevant; etc.
| THEORIES OF CHANGE |  | What are the relationships among strategies, key factors, and conservation targets? What approach will WWF take to advance towards its objectives and goals? Why was this approach chosen over alternatives approaches? Overall, has a complete and coherent picture been painted and does it seem that WWF is engaging at the right 'pressure points' to meet necessary and sufficient conditions for success?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| THEORY OF CHANGE Project contains a clear and sound framework for how strategies will lead to desired results, specifying all key assumptions and relationships of cause and effect; project activities are necessary and sufficient to deliver project Objectives and Goals | The project has described the relationships among conservation targets, threats, opportunities, stakeholders, and WWF strategies that exists and has shown how it will create change through a tool such as a logic model, results chains, Miradi model, concept map, and/or log frame. The tool and its output are being used to ensure logic of strategic approach and clarity of communication to staff, partners and stakeholders. | A theory of change has been described and documentation shows evidence of the theory being tested through a logic tool (e.g. results chains). However this has not been optimally used to communicate the theory internally or to partners/stakeholders etc. externally | A theory of change has been described but it is relatively basic and documentation shows little evidence of the theory being tested through a logic tool. | There is a results chain or similar but it is very basic and/or excludes many key elements, therefore any theory of change derived or tested may lead to perverse outcomes or impacts | There is no logic model or theory of change described.
| OPTIMAL STRATEGIES Project has then prioritised the selected strategies that are optimal in terms of economic/ technical feasibility, affordability, WWF niche, likely impact on biodiversity, livelihoods or footprint, etc | Focal strategies of the project/program are clearly defined/described. Strategies and tactics are optimal and have been selected based upon systematic considerations of feasibility, affordability, WWF niche, wellbeing, likely impact on threats/targets/ footprint, etc. The project identified potential climate smart strategies | Focal strategies are linked, focused, feasible and appropriate. Strategies and tactics have been selected based upon some systematic consideration of feasibility, affordability, WWF niche, likely impact on threats/targets/ footprint, etc. | Focal strategies of the project/program are somewhat well defined but are not clearly justified. | Focal strategies of the project/program are poorly defined and little effort was made to select strategies based upon systematic consideration of feasibility, affordability, WWF niche, likely impact on threats/targets/footprint, etc. | Strategies are not defined.
| Hint: | Evidence to support this section may be found in project plan as results chains or similar graphical or narrative logic tools for modeling theories of change; etc. As well as accompanying strategy assessment; documentation of strategy justification; etc
| GOALS, OBJECTIVES & ACTIVITIES |  | What does bottom line success look like in terms of desired future status of conservation targets? What does success look like in terms of desired future condition of the forces, factors, and actors that affect conservation targets?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| GOALS, OBJECTIVES & ACTIVITIES Project has articulated SMART goals and objectives that describe the desired long-term impacts and outcomes (both short and long-term) of the project. | Goal statements of what success looks like are described for each focal target and their desired future condition (while bearing in mind a changing and uncertain climate. Goals are SMART (specific, measurable, ambitious yet achievable, relevant, time-bound). Objectives describe the desired specific achievements of the project over the next 3-5 years, and are outcome oriented and SMART. Activities are described and correspond to strategies, the activities explicitly describe how they work towards achieving the stated goals and objectives, they have been captured and budgeted appropriately in the workplan. Project considerations: The project has clear, explicit and manageable objectives for gender actions within the project Project considerations: the objectives are aligned with the external donor objectives | Goal statements of what success looks like are described for each focal target and their desired future condition (while bearing in mind a changing and uncertain climate) but don't meet all of the SMART criteria Objectives describe the desired specific achievements of the project over the next 3-5 years. They are SMART and outcome oriented. Activities are described and correspond to strategies, the activities explicitly describe how they work towards achieving the stated objectives. | There are goal and objective statements but they are not fully SMART and they may not be tied explicitly to the desired future condition of conservation targets or threats. Nonetheless, they provide some indication of what the project/program seeks to realise or catalyse. Main activities are described. | There are goal and objective statements but they are poorly articulated. There are no clear (intermediate) objectives which can be tracked. Main activities are described. | There is no single document or framework used by all project staff which sets out the goals and objectives
| Hint: | Evidence to support this section may be found in project plan as an action plan, monitoring plan, log frame, results chain, conceptual models; etc
| MONITORING & EVALUATION ADAPTIVE MANAGEMENT |  | How does WWF know if it is being effective and having desired impacts? How does it use this information to improve its work?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| MONITORING & EVALUATION Project includes an M&E plan with indicators for all goals and objectives that are linked to the sequence of results determined by the project logic; | A good monitoring plan is being implemented, with indicators for all goals and objectives that enable assessment of WWF's effectiveness. Key indicators are robust, by being clear, rule-driven, causally linked, gendered, pro-poor and cross-sectoral. Baseline in place for objectives and goals. Methods allow the voices of partners and community members to be heard and recorded. Innovative tools such as video, testimonials, photography are used. Periodic external evaluations are conducted. Project considerations: The project is collecting/analyzing any data about the role and benefits of ecosystems in building resilience/adaptive capacity of people to climate change | A good monitoring plan exists and is implemented for monitoring, evaluation, and adaptive management. Key indicators for goals and objectives have been defined and are robust.. Baseline in place for objectives and goals. Methods and tools are well designed and resourced, and allow comparable information to be collected over time. Clear and effective division of M&E responsibilities. Periodic external evaluations are conducted that can make use of available monitoring data and analysis. | Monitoring plan exists and is partially implemented. Key indicators defined and prioritised, but may not be fully robust. Baseline in place for objectives. Some consistency between monitoring information collected over time. Periodic external evaluations are the only time that the programme looks for evidence of outcomes and impacts, | Monitoring plan exists but is poorly defined and/ or not properly implemented. Key indicators have not been defined or prioritised, and indicators may not be relevant or robust. One person has all the responsibility for monitoring and evaluation. Feedback from partners and community members is ad hoc and not well recorded. Evaluations are under-resourced. | No plan defining indicators to be monitored. Responsibilities for monitoring not defined; no point person for monitoring.. Only activities are monitored. No evaluations conducted.
| DATA ANALYSIS AND ADAPTIVE MANAGEMENT Projects collects data against indicators defined in monitoring plan; project regularly reviews progress in relation to goals and objectives, checks key assumptions, captures lessons, and adapts actions where necessary | Information generated through M&E is analysed and transformed into simple, evidence based statements that clearly show the difference the project is making and allows assessment of WWF's contribution. . Adaptive managment is taking place and is documented. The theory of change, assumptions and learning/research questions are reviewed and are informing adaptive management practices. M&E information guides decision-making regarding strategy and tactics. Data to support indicators is available, accessible, credible, own-able and disaggregate-able. The perspectives of all stakeholder groups are acknowledged and reflected in analysis. Project staff regularly meet and share experiences and key lessons and meet staff from similar projects. . | The program or project team often uses monitoring data to support decision making and adaptive management, and decisions are documented. Change can be shown relative to the baseline. Data to support indicators (and base-line) are generally available, accessible and credible. Project staff regularly meet and share experiences and key lessons and meet staff from similar programmes. Evidence from partners and community members is regularly gathered. | Project staff (but not partners and community members) involved in analysis and distillation of key lessons. Monitoring data is stored and analysed, and is used to support decision making and adapt strategies. Evidence from the M&E plan captures good success stories from communities and partners but these are ad hoc. | The program or project team rarely uses monitoring data to support decision making and adapt strategies. Analysis of progress towards objectives and goals tends to be subjective, very little evidence to back up claims. Monitoring data is poorly stored and tends to remain in unanalysed form. | No systematic analysis of progress towards objectives and goals (only activities are tracked). Data not stored in a usable form. Project staff on the ground are not invited to analyse and share lessons. Limited evidence that activities are adapted in response to analysis of monitoring data..
| Hint: | Evidence to support this section may be found in project plan as an action plan, monitoring plan, log frame, results chain, conceptual models; etc
| LEARNING & SHARING |  | How does WWF go about gathering, analyzing, documenting, and sharing lessons learned to help improve effectiveness of the project/program and WWF overall? How will WWF go about winning over key audiences? How will it convince key actors to take necessary actions or change behaviors?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| LEARNING & SHARING Project formally reflects and identifies learning and lessons from planning and implementation with stakeholders. Learning is communicated with key internal and external audiences; projects carries out periodic independent evaluations and review exercises and has a culture that encourages good learning and adaptive management practices | Reflection in the programme team and with stakeholders regularly takes place. Learning and lessons are regularly collected, documented, and communicated with key internal and external audiences (including project partners, stakeholders and community members) via appropriate and accessible means. Evidence and learning from the programme inform WWF strategy, communications and advocacy positions internationally. A communication strategy describes how communications will leverage support for both conservation outcomes and marketing/fundraising needs. | Programme teams reflect togther. Some effort is made to document and share learning and lessons learned. Some effort is made to reflect and support a learning culture. . Evidence, learning and lessons learned from WWF projects used to inform the shaping of national or regional policy. There is a communications strategy but it focuses largely on marketing and fundraising. Conservation advocacy aspects are weak. | Ad-hoc effort is made to document and share lessons learned. Ad-hoc effort is made to contribute to a learning culture but little evidence is collected to understand what is working and not working with regards to learning and sharing. There is a communications strategy but it focuses largely on marketing and fundraising. Conservation advocacy aspects are absent | Limited opportunity for project staff and partners to share and learn from each other. Lessons are rarely collected, documented, and are not shared beyond the project team, WWF office and donor.. There is a basic communications strategy but the discussion of the approach to communications is very weak and omits important elements such as conservation advocacy or marketing. | Lessons and evidence not well documented or captured for dissemination. Lessons are not shared beyond the project team. There is no communications strategy.
| RISKS MANAGEMENT, SUSTAINABILITY & EXIT STRATEGY |  | What could prevent success in the immediate or long term? What conditions must be in place for impacts to be sustained even if WWF exits the project?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| RISK MANAGEMENT Project has fully assessed the risks to achieving its objectives and goals, and is taking measures to mitigate them. (To address this, some projects also consider 'key external assumptions' that need to hold true). | The project is grounded in well researched and comprehensive risk analysis and provides good assessment of overall risk level. Risk areas may include Political, Economic, Other Stakeholders, Technical, Capacity, Financial, Environmental Risks to achieving objectives and goals and have been identified. Monitoring tools and workplans includes risk mitigation and making timely adjustments. Risk of negative project impacts is addressed. | The project is grounded in well researched and comprehensive risk analysis and provides good assessment of overall risk level. Monitoring tools and workplans includes risk mitigation and making timely adjustments. | The project has a risk analysis that covers main threats to project objectives. Risk mitigation measures are included in workplans. | Risk factors are somewhat defined but mitigation measures are unclear. | Risk factors have not been defined and are not being addressed. |  | See comment
| SUSTAINABILITY AND EXIT STRATEGY Project includes a strategy to support sustainability of project results and an eventual exit by WWF from some or all activities. | Factors to support sustainability of project results have been defined and actions taken to build these factors into strategies and workplans. Timeframe that should enable WWF and partners to exit responsibly while ensuring sustainability of results has been defined. The desired condition of the sustainability factors (to support an exit by WWF) has been defined, and the factors are being monitored. | Factors to support sustainability of project results have been defined and actions taken to build these factors into strategies and workplans. An exit strategy is generally well defined. | An exit strategy has been discussed but requires more definition or work a plan to address these gaps. And/or exit strategy is defined but not fully documented | An exit strategy has been discussed but is not linked to a consideration of the conditions necessary for sustainability. | Exit strategy is not defined or being addressed
| Hint: | Evidence to support this section may be found in project plan as a risk assessment, consideration of factors for sustainability, formal exit strategy, monitoring plan, log frame, results chain, conceptual models; etc
| CAPACITY DEVELOPMENT |  | Who will get the job done? Do they have, or will they develop, the necessary capacity (knowledge, skills, attitude and opportunity)?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| CAPACITY DEVELOPMENT Project possesses the human resources (staff and skills), support systems (HR, finance, IT, etc), and governance structures needed for the successful implementation of all activities; capacity gaps are filled in a timely manner including those of the project stakeholders | Based on capacity assessment, capacity development strategies have been identified and included in workplans and budgets - for both WWF and partners. Where necessary, partnerships are formalised including agreed expectations, roles and responsibilities, and frameworks for decision-making and communications Governance mechanisms are working effectively, and project team practices strong internal communication and peer to peer sharing. The project leader and key team members have the necessary skills to apply all steps of the WWF Network Standards. | Human resource requirements have been defined through a capacity assessment, both internal resources and those via partnerships either formal or informal. Governance mechanisms are defined in both an internal and external context. There is significant effort to meet these needs and some allocation of budget. Project team has clear roles, responsibilities and processes for effective decision making | Human resource requirements and governance mechanisms are generally defined but only for the internal project team. There is some effort to meet these needs of the internal teams capacity gaps and some allocation of budget | There is limited understanding of human resource requirements and governance mechanisms. How these needs are being met is mostly unclear. | Human resource needs are not defined and there is evidence that they are not being met.
| STRATEGIC PARTNERSHIPS (GOVERNMENT/ PUBLIC INSTITUTION/ PRIVATE SECTOR BEHAVIOUR) (There may be several strategic partners; please provide an average score and comment briefly on differences between partners) | As under level 4 plus: Partner is exhibiting, through its statements and actions, ownership and commitment to objectives consistent with the project. Partner is providing political and counterpart management support for the project. Partner has the necessary capacity to conduct its work as a project partner. WWF and partner/s are able to have open and regular dialogue on progress, reflecting on both organisation’s contributions | WWF has strategies to influence and collaborate with the institution in order to better align policies, commitments and actions with the project (including provision of necessary capacity-building and technical support). Partner is exhibiting commitments such as quality policies or funding that are supportive of the project's objectives. | WWF has strategies to influence and collaborate with the institution in order to better align policies, commitments and actions with the project. Partner is exhibiting commitment in principle that are supportive of the project's objectives. | WWF has identified key partners and strategies to engage, but engagement is currently limited | WWF has no clear strategy to engage and collaborate with key partners.
| Hint: | Evidence to support this section may be found in a project plan, capacity assessment, risk assessment, exit strategy, monitoring plan, log frame, results chain, conceptual models, workplans, budgets, partnership TORs, organigrammes; etc.
| FINANCE |  | What funds do WWF and partners need? What does the project have, and how will it address any gaps? Is the project delivering good value?
| Score: | 5 | 4 | 3 | 2 | 1 | Rating | Comment
| BUDGET Project contains a clear budget identifying the financial resources over the lifetime of the project necessary to implement all activities; budget includes necessary provisions for salaries, coordination, training, and M&E costs. M&E costs of a project should normally range from 5-10% (up to 30% for pilot projects) | A detailed budget identifies the financial resources required over the lifetime of the project necessary to implement all activities; budget includes necessary provisions for salaries, coordination, training, M&E, and reflection and learning costs. | Detailed budgets exist for the current project phase, consistent with the workplan and including M&E costs. The budget is adhered to and reviewed consistently through the project | Budgets exist but are basic or missing some key elements. Budget is reviewed and assessed periodically | There is a budgets but they it is extremely basic or poorly done. | There are no workplans or budgets.
| FUNDING and SUPPORT The scale of funding secured for the project is consistent with the scale of ambition identified in the project budget. Levels of support are adequate for the project to accomplish its aims | The scale of funding secured is consistent with the budget. Funding is sufficient or flexible enough to allow for quality project planning, M&E, capacity strengthening, and adaptive management. Longer term funding prospects and plans (where necessary) are in place. The level of support received by external partners or internally is helping to achieve widening or deepening impact and/or is helping to lever funds from elsewhere. Appropriate and timely management support is provided from governing/senior management bodies. | The scale of funding secured is close to the requirements of the ambition identified by the project. Appropriate steps are being taken to acquire necessary funding to meet the funding gap or to scale down the level of ambition. Appropriate and timely management support is provided from governing/senior management bodies. | The scale of funding secured for the project/program is nearly consistent with the budget. Some effort is being made to address the gap and scale down the level of ambition. Management support is generally adequate to support adaptive action. | The scale of funding secured for the project/program appears insufficient. Very little effort is being made to address gaps or scale down the level of ambition. | There is no information on funding needs or fundraising strategy.
Note on C24: Will Beale: For level 5, specific climate change risks/hazards should be set out in the threat anaylsis (the risks and hazards should be based on trends AND projections).
Note on C26: Will Beale: To declare Level 5 you will need evidence to substantiate this which should supply that detail (e.g. type of methodologies used to assess impact on poor and marginalised, feedback on project through participatory consultation)
Note on I51: Will Beale: State here the main risks identified (no more than 3) and assess the level of those risks as Low, Modest, Significant or High
Note on C52: Will Beale: Many of the factors to support sustainability should be addressed through sound application of each step of the adaptive management cycle. An exit strategy requires an explicit definition of the conditions that will need to be reached for a responsible exit to be possible e.g. with respect to stakeholder ownership and capacity, policy environment, socio-cultural issues, finance, climate resilience etc.

## Instructions
Instructions for Good Practice Project Management Self Assessment Tool
"Factors of Performance" are the key practices, processes, systems or behaviours at the project, office or Network level, or those that are exhibited by external partners, that influence the ability of a project or programme to achieve its goals and objectives. It is useful to tracking these factors of performance as they translate to challenges or strengths a project encounters as it seeks to progress.
The Excel-based self assessment tool is intended to:
1) help an individual project or programme to better understand the quality of its practices, and the challenges and strengths that it faces, and hence to take appropriate adaptive action.
2) support projects and programmes to share this understanding via a common framework. This may be particularly useful for projects or programmes that are closely related.
3) support the broader analysis of how WWF can improve its effectiveness, and help us to show any improvements in the quality of WWF’s work.
Ratings against individual criteria ‘roll up’ automatically to overall ratings against the factors. In relation to Technical Reporting, specific issues for attention should be noted in section 3 of Part 1 (Challenges and Strengths Affecting Performance) and you should outline appropriate adaptive actions in section 4 of Part 1. It is strongly recommended to include a summary table such as the one below.
From one self-assessment to the next, make sure to highlight in the table any important changes in your ratings.
Factor | Rating (from 1-5) | Specific issues for attention
Design
Monitoring, Evaluation and Learning
Capacity & Finance
Beneficiaries and Indigenous People
Strategic Partnerships (Government/ Private Sector)
Risk Management and Sustainability
Value for Money
The tool can also be used to help review the quality of strategic plans and project proposals. To that end, it incorporates a second tab (Top 5’s) to help identify the main strengths and areas for improvement, and to record and share improvements made. This second tab does not need to be completed and submitted as part of a technical report unless the project team wishes to do so.

## Top 5's
What are the Top 5 elements that you think are good | Why | Will you be sharing these or doing it again? | How did it go? | Any lessons learned & do you plan to share these?
What are the Top 5 issues that you'd like to see improved in the programme management/ plan? | Why | Can you do something about this and if so what? | How did it go? | Any lessons learned & do you plan to share these?